## User Stories
Epic | User Story | Expected Time (hrs) | Actual Time (hrs) | Status
Epic 1: AI Solver | User Story 1.1 — Versus AI Solver Mode | 1 | 0.25 | Complete
Epic 1: AI Solver | User Story 1.2 — Difficulty Selection | 1 | 1 | Complete
Epic 1: AI Solver | User Story 1.3 — Easy, Medium, Hard Difficulty Curve | 5 | 10.25 | Complete
Epic 1: AI Solver | User Story 1.4 — Taking Turns | 3 | 2.25 | Complete
Epic 1: AI Solver | User Story 1.5 — Game Win | 1 | 1 | Complete
Epic 1: AI Solver | User Story 1.6 — Game Loss | 1 | 1 | Complete
Epic 2: Custom Feature – Timer | User Story 2.1 — Timer Display | 2 | 2 | Complete
Epic 3: Project Delivery & Compliance | User Story 3.1 — Code Freeze | 1 | 1 | Complete
Epic 3: Project Delivery & Compliance | User Story 3.2 — Weekly Demos | 0.5 | 0.5 | Complete
Epic 3: Project Delivery & Compliance | User Story 3.3 — Documentation & Peer Reviews | 5 | 3.25 | Complete
Epic 4: Bugfixes | User Story 4.1 — Flag Behavior | 1 | 0.5 | Complete
Epic 4: Bugfixes | User Story 4.2 — Win/Loss/Draw Behavior | 0.5 | 0.5 | Complete

## Group Meetings
Date | Meeting | Length (Hours)
2025-09-22 | Project 2 Brainstorming | 1
2025-09-24 | Project 2 Planning | 0.75
2025-09-29 | GTA Meeting | 0.75
2025-10-01 | Finish Project 2 | 1.25

## Bryson Toubassi
Date | Task Description | Time Worked (Hours)
2025-10-01 | Testing | 0.25
2025-10-02 | Fix Flag and Cell Click bugs | 0.5
2025-10-05 | Updated System Architecture Document | 0.5

## Matthew Eagleman
Date | Task Description | Time Worked
2025-09-29 | Copied project repo, began working on AI Solver | 0.75
2025-10-01 | Created AI difficulty Dropdown menu, fixed some bugs, Made easy and medium AI | 5
2025-10-02 | Fixed various bugs, moved Medium and Easy AI's to the AI solver | 1

## Owen Berkholtz
Date | Task Description | Time Worked
2025-09-30 | Create User Stories Document | 1
2025-10-01 | Fix bug that prevented player from winning | 0.5
2025-10-02 | Create Time-Keeping Method Document | 0.25
2025-10-02 | Add Final Time to Victory/Loss Screen | 0.25

## Connor Anderson
Date | Task Description | Time Worked (Hours)
2025-09-26 | Fix indentation error, add git ignore file | 2
2025-09-29 | GitHub Changes | 0.5
2025-10-01 | Testing | 0.25
2025-10-01 | Add Taking Turns and AI Solver Skeleton | 2.25
2025-10-02 | Finish User Stories Document | 0.25
2025-10-02 | Start Updated UML Class Diagram | 0.25
2025-10-02 | Testing and Fix Win/Loss messages | 0.5
2025-10-02 | Merge and Test Hard AI Changes | 0.25
2025-10-03 | Fix Win/Loss/Draw conditions and conduct testing | 1
2025-10-03 | Merge latest hard ai into dev, re-add incrementing turns, and test | 1
2025-10-05 | Finish UML Class Diagram | 0.5

## Mohamed Ashraq
Date | Task Description | Time Worked (Hours)
2025-10-02 | Created Hard AI Solver | 5
2025-10-03 | Testing all AI solver difficulties | 0.25
2025-10-05 | Code Documentation for hard AI solver | 0.25